## Description of Project
Description of the Project
HealthHub is a cutting-edge healthcare platform that transforms interactions with healthcare providers and the management of personal well-being. It offers individualized health assessments with insights and proactive recommendations based on consumers' needs, utilizing advanced analytics and machine learning. Its telehealth function makes it easier to have virtual consultations with medical specialists, promising fast service delivery. For thorough health monitoring, users can connect data from wearable devices, track medication adherence, and securely maintain medical records. While AI-driven forecasts indicate possible health hazards for preemptive action, interactive challenges and rewards encourage healthy lifestyles.

## Versions
1. Version 1 | Responsibles | Release Date of Versions
Login With pasword (v1.0) | Talha Shahzad | v1.0 - 17.3.2024
Keeping member records (v1.0) | Talha Shahzad | v1.0 - 18.3.2024
Keeping personnel information (v1.1) | Talha Shahzad | v1.0 - 19.3.2024
2. Version 2 | Responsibles | Release Date of Versions
Risk Analysis (v2.0) | Talha Shahzad and Husnain Ali | v2.0 - 20.3.2024
Personal Insights (2.0) | Talha Shahzad and Husnain Ali | v2.0 - 21.3.2024
Get Recommendations (2.1) | Talha Shahzad and Husnain Ali | v2.0 - 25.3.2024
Review past journey (v2.1) | Talha Shahzad and Husnain Ali | v2.0 - 26.3.2024
3. Version 3 | Responsibles | Release Date of Versions
Remote device integration (v3.0) | Ali Khizar | v3.0 - 27.03.2024
Test Result Accessibility (v3.1) | Ali Khizar | v3.1 - 28.03.2024
Report (v.1) | Ali Khizar | v3.1 - 28.03.2024

## Product Backlog
Product Backlog
User Stories
Situation | Name | Description | Point
Done | Login with Password | As a user I want to view my health analytics so that I can take rational choices and maintain my well-being | 6
Done | Risk Analysis | As a user I want to receive my health status and risk factor so that I can keep record of my health stats and devise a plan accordingly. | 8
Done | Get Recommendations | As a user I want to get recommendations from the system according to my health stats so that I can get a better health plan. | 4
Done | Virtual Consultions | As a user, I want to schedule virtual consultations with healthcare professionals through HealthHub's telehealth feature to obtain medical advice and treatment conveniently. | 5
Done | Data Storage Protection | As a user, I want to securely store my medical records within Health Hub so that I can maintain a centralized repository of my health information at any time. | 2
Done | Test Result Accessibility | As a user, I want to access my test results in HealthHub so that I can compare my past medical test history and evaluate the changes in result. | 6
Done | Review past journey | As a user, I want to access treatment plans stored in HealthHub so that I can review my past track of my ongoing healthcare journey and devise a new plan based on that. | 5
Done | Reporting | As a user, I want to share specific medical records with my healthcare providers through HealthHub so that to facilitate continuity of care and informed decision-making | 4
Done | Personal Insight | As a user of HealthHub, I want the platform to analyze my health data to provide me with personalized insights into my health risks and challenges | 1
Done | Remote device integration | As a user, I want to get my real-time health insights while using wearable or other monitoring devices so that it collects and evaluate different activity levels or sleep patterns for health plans | 4
It is cancelled | Manage Stress level | As a busy professional, I want quick access to health education and resources for stress management techniques so that I can manage my stress level and improve my overall wellbeing. | 0

## Board
STORIES | NOT DONE | THE UNDER CONSTRUCTION | DONE | IT IS CANCELLED
STORY # 03:
Login with Password
STORY # 02:
Risk Analysis
STORY # 02 - DUTY# 04: Tablo oluşturulması
STORY # 01-- DUTY # 03: Relationship between login and signup
STORY # 01 - - DUTY # 01: user interface
STORY # 03- DUTY # 01: Kullanıcı arayüzü
STORY # 03-DUTY # 02: Veri girişi
STORY # 04 -DUTY # 01: Kullanıcı arayüzü
STORY # 04- DUTY # 02: Veri girişi
STORY # 02 - DUTY # 02: Veri girişi
STORY # 02 - DUTY# 01: Kullanıcı arayüzü
STORY # 01 - DUTY# 02: Data input
STORY #03:
Get Recommendations
STORY #04::
Virtual Consultions
STORY #05:
Data Storage Protection
STORY #06:
Test Result Accessibility
STORY #07:
Review past journey
STORY #08:
Reporting
STORY #09:
Remote device integration
STORY # 01 - DUTY# 04
Creating a tuser
STORY # 03 - DUTY# 04: Tablo oluşturulması
STORY # 02- - DUTY # 03: Üye tablosu ile diğer tablolar arası ilişkiler
STORY # 03-- DUTY# 03: Malzeme tablosu ile diğer tablolar arası ilişkiler
STORY # 05 - DUTY# 01: Kullanıcı arayüzü
STORY # 05- DUTY# 02: Veri girişi
STORY # 06 - DUTY # 01: Kullanıcı arayüzü
STORY # 06- DUTY # 02: Veri girişi
STORY # 07- DUTY# 02: Veri girişi
STORY # 07 -DUTY # 01: Kullanıcı arayüzü
STORY # 08 DUTY# 01: Kullanıcı arayüzü
STORY # 09 - DUTY 01: Kullanıcı arayüzü
STORY # 09 - GÖREV #04
Password uniqueness
STORY # 04-- DUTY # 03: Bütçe tablosu ile diğer tablolar arası ilişkiler
STORY # 05- DUTY # 03: Ürün tablosu ile diğer tablolar arası ilişkiler
STORY #10:
Personal Insight
STORY # 06- DUTY # 03: Ölçüm tablosu ile diğer tablolar arası ilişkiler
STORY # 07- DUTY # 03: Aktivite tablosu ile diğer tablolar arası ilişkiler
STORY #11:
Manage Stress level
STORY #11 stress Schedulenme
STORY # 04 -- DUTY# 04
Tablo oluşturulması
STORY # 05- DUTY# 04
Tablo oluşturulması
STORY # 06 DUTY # 04
Tablo oluşturulması
STORY # 07 DUTY# 04
Tablo oluşturulması
STORY # 08- DUTY # 02
Görüntülenmesi istenen rapor türleri belirlendi.
STORY # 09 - DUTY# 01: Kullanıcı arayüzü
STORY # 09- DUTY # 03
Şifre formatı belirlendi.
STORY # 09DUTY# 02: Şifre giriş ekranı

## BurnDown
BURNDOWN CHART
Project | Story | Beginning | 2024-04-21 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04
HealthHub | Create Interfaces | 4 | 7 | 2 | 2 | 2 | 2 |  |  |  |  | 0
HealthHub | Register FYP Groups | 3 | 4 | 1 | 1 | 2 | 1 | 1 | 1 |  |  | 0
HealthHub | Frontend | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
HealthHub | Evaluation Forms | 3 | 3 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 0
HealthHub | Reviews | 3 | 1 | 4 | 2 | 2 | 1 | 1 |  |  |  | 0
HealthHub | View Grades/Information | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 0 |  |  | 0
HealthHub | Assign Assessments/Submission | 2 | 2 | 3 | 3 | 1 | 1 |  |  |  |  | 0
HealthHub | View Missing Reviews | 2 | 1 | 2 | 1 | 1 | 2 | 1 |  | 2 |  | 0
HealthHub | Reporting | 4 | 2 | 4 | 2 |  | 2 |  | 2 |  | 2 | 0
HealthHub | Responsive | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Ideal - Remaining time working hours |  | 31 | 27.9 | 24.8 | 21.7 | 18.6 | 15.5 | 12.4 | 9.3 | 6.2 | 3.1 | -4.4409e-15
Actual - Remaining time working hours |  | 31 | 28 | 27 | 20 | 16 | 17 | 10 | 7 | 6 | 6 | 0
Note on E5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on F5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered